## EBS - WORKPLAN
Tentative Date
Title: STRENGTHENING SURVEILLANCE, DISEASE INTELLIGENCE, AND HEALTH INFORMATION EXCHANGE Scope: The project has five objectives of which two (2&5) are being implemented by SACIDS Foundation for One Health Objective 2: To support EBS implementation pilot and scale-up in Member States Objective 5: To implement core activities of Africa CDC’s strategy to address antimicrobial resistance.
1 | Cross-Cutting Activities
| 1.1 | Project Protocol development | Feb
| 1.2 | Planning Meeting | Feb
| 1.3 | Inception Workshop | Feb
2 | EBS : Output 1: Develop training materials, including for training-the-trainer, based on Africa CDC technical guidelines for EBS.
| 2.1 | User challenge workshop - test training materials | Feb
| 2.2 | Produce print ready training manual | Feb
| 2.3 | Translate trainig material | Feb
| 2.4 | Develop online guided training courses on EBS and develop online repository | Mar
3 | EBS : Output 2: Conduct training workshops on EBS in conjunction with the various RCCs.
| 3.1 | East Africa | Apr
| 3.2 | Central Africa | May
| 3.3 | Southern Africa | Jun
4 | EBS : Output 3: Provide focused technical support to selected countries to initiate EBS consistent with Africa CDC guidelines.
| 4.1 | Needs assessment / situational analysis - desk work | Mar
| 4.2 | Advcocacy meetings at National level and Liase with implementation partners to seek synergies | Mar
| 4.3 | Re-package Technology based toolkit to facilitate EBS uptake | Feb - Apr
| 4.4 | Support countries to initiate EBS by adopting Africa CDC guidelines | Apr - Dec
5 | AMR : Output 1 : Conduct in person and virtual workshops to develop evidence based guidelines for clinicians to treat susceptible and resistant infections in humans in Africa
| 5.1 | Provide expert support to working group (Africa CDC and CDDEP) review and improve the guidelines | Jan - Dec
6 | AMR : Output 2 : Conduct in person and virtual workshops to develop policy proposals that can be submitted to the AUC for official endorsement of IPC
| 6.1 | Convene regional workshops in Egypt | May
| 6.2 | Convene regional workshops in Zambia | April
| 6.3 | Review of existing policies on antimicrobial use in agriculture/ food production in Africa and current practices and barriers to AMU | Feb - June
7 | AMR : Output 3 : Based upon stakeholder consultation publish a concept paper that describes barriers to prudent AMU in agriculture and industry in Africa and propose policy or other solutions to promote prudent AMU in these settings
| 7.1 | Nairobi: RCCS training workshops for CSOs. 25- 30 participants i.e CSOs | Feb
| 7.2 | Gabob: RCCS training workshops for CSOs. 25- 30 participants i.e CSOs | April
8 | AMR : Output 4 : Develop a detailed and costed plan for strengthening HR for AMR surveillance in Africa
| 8.1 | Conduct cost analysis for HR IPC and /or AMR surveillance activities | Apr - June